## Sheet1
| Project Name | Project Duration | Project Start Date | Project End Date
| CCS Project | 10 weeks | 2019-06-17 | 2019-08-25
Task | Task Description | Task Duration | Task Start Date | Task End Date | 2019-06-17 | 2019-06-24 | 2019-07-01 | 2019-07-08 | 2019-07-15 | 2019-07-22 | 2019-07-29 | 2019-08-05 | 2019-08-12 | 2019-08-19 | 2019-08-26 | 2019-09-02
ID |  |  |  |  | - 21-Jun | - 28-Jun | - 5-Jul | - 12-Jul | - 19-Jul | - 26-Jul | - 2-Aug | - 9-Aug | - 16-Aug | - 23-Aug | - 30-Aug | - 6-Sep
1 | Project Management/Planning
| Feasibility report | one week | 2019-06-17 | 2019-06-21 | bar: 2019-06-17
| Scheduling | two weeks | 2019-06-17 | 2019-06-28 | bar: 2019-06-17 to 2019-06-24
| Project Scope Definition | one week | 2019-06-24 | 2019-06-28 | bar: 2019-06-24
| Project Requirement Definition | one week | 2019-06-24 | 2019-06-28 | bar: 2019-06-24
| Cost Estimation | one week | 2019-06-24 | 2019-06-28 | bar: 2019-06-24
| Risk Analysis | one week | 2019-06-24 | 2019-06-28 | bar: 2019-06-24
| PM Plan Development | one week | 2019-06-24 | 2019-06-28 | bar: 2019-06-24
2 | Software Requirement Specification
| Software Requirements Definition | one week | 2019-07-01 | 2019-07-05 | bar: 2019-07-01
| Delivery Platform Selection | one week | 2019-07-01 | 2019-07-05 | bar: 2019-07-01
| Development Tools Selection | one week | 2019-07-01 | 2019-07-05 | bar: 2019-07-01
| SRS Document Development | one week | 2019-07-01 | 2019-07-05 | bar: 2019-07-01
3 | System Design
| Component Architecture | one week | 2019-07-08 | 2019-07-12 | bar: 2019-07-08
| System Modelling | one week | 2019-07-08 | 2019-07-12 | bar: 2019-07-08
| Database Design | one week | 2019-07-08 | 2019-07-12 | bar: 2019-07-08
| Interface Design | one week | 2019-07-08 | 2019-07-12 | bar: 2019-07-08
| Algorithm/Coding | two weeks | 2019-07-08 | 2019-07-19 | bar: 2019-07-08 to 2019-07-15
4 | System Implementation
| Database Implementation | one week | 2019-07-22 | 2019-07-26 | bar: 2019-07-22
| Interface Implementation | one week | 2019-07-22 | 2019-07-26 | bar: 2019-07-22
| Code documentation | one week | 2019-07-22 | 2019-07-26 | bar: 2019-07-22
5 | Verification and Test
| System Testing | one week | 2019-07-29 | 2019-08-02 | bar: 2019-07-29
| User Testing | one week | 2019-07-29 | 2019-08-02 | bar: 2019-07-29
| System Rework | one week | 2019-07-29 | 2019-08-02 | bar: 2019-07-29
| Testing Environment Training | two weeks | 2019-07-29 | 2019-08-13 | bar: 2019-07-29 to 2019-08-12; 2019-08-26 to 2019-09-02
6 | System Deployment
| System Set Up | one week | 2019-08-16 | 2019-08-20 | bar: 2019-08-19
7 | Software Maintenance
| Software Maintenance Plan Development | one week | 2019-08-23 | 2019-08-27 | bar: 2019-08-26
8 | Prject Close Out
| Summative Evaluation | one week | 2019-08-30 | 2019-09-03 | bar: 2019-09-02
| Notes Release | one week | 2019-08-30 | 2019-09-03 | bar: 2019-09-02
| Buffer time | two week | 2019-08-26 | 2019-09-06
Formulas:
Project End Date = [Project Start Date]+4
Project End Date = [Project End Date, row above]+11
Project Start Date = [Project Start Date, row above]